## Dashboard
Microsoft Autopilot Project Dashboard - Updated
Project Overview | Critical Applications
Total Tasks: | Security Apps (CrowdStrike, Absolute):
Completed Tasks: | VPN & Authentication Apps:
In Progress Tasks: | Security Policies Applied:
Not Started Tasks:
Project Progress: | Phase Progress
Phase 1 (Infrastructure):
Issue Summary | Phase 2 (Apps & Policies):
Open Issues: | Phase 3 (Device Naming):
In Progress Issues: | Phase 4 (Co-management):
Critical Issues:
High Priority Issues: | Feasibility Testing & Deployment Modes
User-Driven Feasibility:
Resource Utilization | Deployment Mode Framework:
Total Estimated Hours: | Pre-Provisioning Testing:
Total Actual Hours:
Hours Variance: | Critical Success Metrics
Critical Tasks Completed:
Security Issues Open:
Feasibility Issues Open:

## Task Tracking
Task ID | Phase | Task Name | Description | Owner | Status | Priority | Start Date | Due Date | Completion Date | % Complete | Estimated Hours | Actual Hours | Dependencies | Notes
T001 | Phase 1 | Verify Azure AD Premium Licensing | Confirm sufficient P1/P2 licenses for Autopilot | Infrastructure Team | Not Started | High | 2024-02-07 | 2024-02-09 |  | 0 | 4 | 0 |  | Check current license count
T002 | Phase 1 | Validate Intune Licensing | Ensure device licenses available | Infrastructure Team | Not Started | High | 2024-02-07 | 2024-02-09 |  | 0 | 2 | 0 | T001
T003 | Phase 1 | Install Intune Connector | Install connector on pre-prod server | Infrastructure Team | Not Started | Critical | 2024-02-10 | 2024-02-14 |  | 0 | 8 | 0 | T001,T002 | Requires domain admin access
T004 | Phase 1 | Configure Service Account | Create dedicated service account with domain join permissions | Security Team | Not Started | Critical | 2024-02-10 | 2024-02-12 |  | 0 | 4 | 0
T005 | Phase 1 | Test Connector Communication | Verify connector can communicate with Intune | Infrastructure Team | Not Started | High | 2024-02-13 | 2024-02-14 |  | 0 | 3 | 0 | T003,T004
T006 | Phase 1 | Autopilot Mode Feasibility Assessment | Test User-Driven vs Pre-Provisioning deployment modes | QA Team | Not Started | Critical | 2024-02-12 | 2024-02-18 |  | 0 | 20 | 0 | T005 | Test 15-20 devices each mode
T007 | Phase 1 | Network Connectivity Testing | Test VPN and hybrid join across user locations | Network Team | Not Started | High | 2024-02-15 | 2024-02-19 |  | 0 | 12 | 0 | T006 | Test multiple scenarios
T008 | Phase 1 | User Experience Validation | Conduct UAT with representative user groups | QA Team | Not Started | High | 2024-02-16 | 2024-02-20 |  | 0 | 16 | 0 | T006 | Different skill levels
T009 | Phase 1 | Deployment Mode Decision Matrix | Create framework for mode selection | Project Manager | Not Started | Critical | 2024-02-19 | 2024-02-21 |  | 0 | 8 | 0 | T006,T007,T008 | Document decision criteria
T010 | Phase 2 | Package CrowdStrike Windows Sensor | Create Win32 app with organization CID | Security Team | Not Started | Critical | 2024-02-22 | 2024-02-26 |  | 0 | 12 | 0 | T009 | Must install before domain join
T011 | Phase 2 | Package Cisco Secure VPN Client | Create Win32 app for VPN deployment | Network Team | Not Started | Critical | 2024-02-22 | 2024-02-26 |  | 0 | 10 | 0 | T009 | Pre-logon capability required
T012 | Phase 2 | Configure VPN Certificates | Deploy machine certificates for VPN auth | Security Team | Not Started | Critical | 2024-02-24 | 2024-02-28 |  | 0 | 8 | 0 | T011
T013 | Phase 2 | Package Absolute Agent | Create Win32 app with server settings | Security Team | Not Started | High | 2024-02-26 | 2024-03-02 |  | 0 | 6 | 0 | T010
T014 | Phase 2 | Package Duo for Windows Logon | Configure with integration keys | Security Team | Not Started | High | 2024-02-27 | 2024-03-05 |  | 0 | 8 | 0
T015 | Phase 2 | Package EPASS | Password management app with domain dependency | Application Team | Not Started | Medium | 2024-03-01 | 2024-03-07 |  | 0 | 6 | 0 |  | Domain join required
T016 | Phase 2 | Configure Company Portal | Setup with corporate branding | Application Team | Not Started | High | 2024-02-26 | 2024-03-02 |  | 0 | 4 | 0
T017 | Phase 2 | Package Chrome Browser | Enterprise policies and configuration | Application Team | Not Started | Medium | 2024-03-03 | 2024-03-07 |  | 0 | 4 | 0
T018 | Phase 2 | Windows Enterprise Edition Policy | Create upgrade policy from Pro to Enterprise | Infrastructure Team | Not Started | Critical | 2024-02-24 | 2024-02-28 |  | 0 | 6 | 0 | T009 | Must run early in Autopilot
T019 | Phase 2 | CIS Baseline Policies | Import and configure Level 1 baseline | Security Team | Not Started | High | 2024-02-26 | 2024-03-04 |  | 0 | 12 | 0
T020 | Phase 2 | Defender Onboarding Package | Deploy organization-specific package | Security Team | Not Started | Critical | 2024-02-27 | 2024-03-05 |  | 0 | 8 | 0
T021 | Phase 2 | Defender AV and Firewall Config | Configure real-time protection and firewall | Security Team | Not Started | High | 2024-03-01 | 2024-03-07 |  | 0 | 6 | 0 | T020
T022 | Phase 2 | USB Storage Restrictions | Evaluate and configure access controls | Security Team | Not Started | Medium | 2024-03-03 | 2024-03-09 |  | 0 | 4 | 0 |  | Business approval needed
T023 | Phase 3 | Design Device Naming Convention | Establish naming standards and templates | Infrastructure Team | Not Started | High | 2024-03-08 | 2024-03-12 |  | 0 | 8 | 0 | T022
T024 | Phase 3 | Create Autopilot Profiles by Department | IT, HR, Finance, Executive profiles | Infrastructure Team | Not Started | High | 2024-03-10 | 2024-03-14 |  | 0 | 12 | 0 | T023
T025 | Phase 3 | Develop PowerShell Naming Script | Fallback script for custom naming | Infrastructure Team | Not Started | Medium | 2024-03-12 | 2024-03-16 |  | 0 | 8 | 0 | T023
T026 | Phase 3 | Create IT Depot Manual Procedure | Backup manual naming process | Process Team | Not Started | Low | 2024-03-13 | 2024-03-17 |  | 0 | 4 | 0 | T023
T027 | Phase 3 | Test Device Naming Scenarios | Test all naming approaches | QA Team | Not Started | High | 2024-03-15 | 2024-03-19 |  | 0 | 8 | 0 | T024,T025
T028 | Phase 3 | Validate Deployment Mode Assignments | Apply decision matrix to test scenarios | Project Manager | Not Started | High | 2024-03-17 | 2024-03-21 |  | 0 | 6 | 0 | T027 | Ensure correct mode selection
T029 | Phase 4 | Enable Co-management in SCCM | Configure SCCM for co-management | SCCM Team | Not Started | High | 2024-03-20 | 2024-03-24 |  | 0 | 6 | 0 | T028
T030 | Phase 4 | Package SCCM Client | Create Intune app for SCCM client | SCCM Team | Not Started | Critical | 2024-03-22 | 2024-03-26 |  | 0 | 10 | 0 | T029
T031 | Phase 4 | Configure Application Sequencing | Set installation order for all apps | Application Team | Not Started | High | 2024-03-24 | 2024-03-28 |  | 0 | 8 | 0 | T030
T032 | Phase 4 | Test Pre-Provisioning Workflow | Validate white glove deployment process | QA Team | Not Started | High | 2024-03-26 | 2024-04-01 |  | 0 | 16 | 0 | T031 | For devices requiring this mode
T033 | Phase 5 | Security Application Testing | Test CrowdStrike, Absolute, Defender deployment | Security Team | Not Started | Critical | 2024-03-29 | 2024-04-05 |  | 0 | 24 | 0 | T032 | Test 10 devices each mode
T034 | Phase 5 | VPN and Authentication Testing | Test VPN, Duo, domain join process | Network Team | Not Started | Critical | 2024-04-01 | 2024-04-08 |  | 0 | 20 | 0 | T032
T035 | Phase 5 | Device Naming Validation | Verify all naming conventions work | Infrastructure Team | Not Started | High | 2024-04-03 | 2024-04-09 |  | 0 | 12 | 0 | T033,T034
T036 | Phase 5 | Deployment Mode Performance Testing | Compare User-Driven vs Pre-Provisioning metrics | QA Team | Not Started | High | 2024-04-05 | 2024-04-11 |  | 0 | 16 | 0 | T035 | Timing and success rates
T037 | Phase 5 | End-to-End Pilot Testing | Complete deployment testing | QA Team | Not Started | Critical | 2024-04-08 | 2024-04-15 |  | 0 | 40 | 0 | T036 | 20 pilot devices - mixed modes
T038 | Phase 5 | Performance Optimization | Optimize deployment speed and reliability | Infrastructure Team | Not Started | Medium | 2024-04-10 | 2024-04-16 |  | 0 | 16 | 0 | T037
T039 | Phase 6 | Security Team Training | Train on new security applications | Security Team | Not Started | High | 2024-04-15 | 2024-04-19 |  | 0 | 8 | 0 | T038
T040 | Phase 6 | Help Desk Training | Train on Autopilot troubleshooting | Training Team | Not Started | High | 2024-04-17 | 2024-04-21 |  | 0 | 12 | 0 | T038 | Include deployment mode decision tree
T041 | Phase 6 | Production Rollout Strategy | Implement deployment mode assignments | Project Manager | Not Started | Critical | 2024-04-19 | 2024-04-25 |  | 0 | 20 | 0 | T039,T040 | Apply decision matrix
T042 | Phase 6 | Phased Production Rollout | Deploy by department phases | Project Manager | Not Started | Critical | 2024-04-22 | 2024-05-06 |  | 0 | 60 | 0 | T041 | All departments - mixed modes
T043 | Phase 6 | Monitoring Dashboard Setup | Create deployment monitoring | Infrastructure Team | Not Started | Medium | 2024-04-24 | 2024-04-28 |  | 0 | 12 | 0 | T042 | Track mode-specific metrics
T044 | Phase 6 | Documentation Finalization | Complete all project documentation | Documentation Team | Not Started | Medium | 2024-04-29 | 2024-05-03 |  | 0 | 16 | 0 | T043 | Include decision matrix procedures

## Issue Tracking
Issue ID | Date Reported | Reported By | Issue Title | Description | Category | Severity | Priority | Status | Assigned To | Related Task ID | Root Cause | Resolution | Date Resolved | Resolution Time (Hours) | Follow-up Required | Notes
I001 | 2024-02-08 | John Smith | CrowdStrike Package Installation Failed | CrowdStrike sensor fails to install during Autopilot | Security Applications | Critical | Critical | Open | Security Team | T010 |  |  |  |  | Yes | May need manual CID configuration
I002 | 2024-02-12 | Jane Doe | VPN Certificate Deployment Issue | Machine certificates not deploying to test devices | Security | High | High | In Progress | Security Team | T012 | Certificate template permissions |  |  |  | No | Working with CA team
I003 | 2024-02-15 | Mike Johnson | Windows Enterprise Upgrade Failure | Devices not upgrading from Pro to Enterprise | System Configuration | Critical | Critical | Open | Infrastructure Team | T018 |  |  |  |  | Yes | License key may be invalid
I004 | 2024-02-18 | Sarah Wilson | Autopilot Profile Assignment | Devices getting assigned to wrong department profile | Device Management | Medium | High | Open | Infrastructure Team | T024 |  |  |  |  | No | Review group targeting rules
I005 | 2024-02-20 | David Brown | Duo Installation Timing | Duo installing before domain join causing issues | Authentication | Medium | Medium | Open | Security Team | T014 |  |  |  |  | No | Need to adjust installation sequence
I006 | 2024-02-22 | Lisa Garcia | CIS Baseline Policy Conflicts | Some CIS policies conflicting with app installations | Security Policies | High | High | Open | Security Team | T019 |  |  |  |  | Yes | May need policy exceptions
I007 | 2024-02-24 | Tom Anderson | Device Naming Character Limit | Some department codes exceed 15-character limit | Device Naming | Medium | Medium | Open | Infrastructure Team | T023 |  |  |  |  | No | Need shorter department codes
I008 | 2024-02-25 | Amy Chen | Absolute Agent Silent Install | Absolute Agent not installing silently | Security Applications | Medium | Low | Open | Security Team | T013 |  |  |  |  | No | Check installation parameters
I009 | 2024-02-14 | Mark Rodriguez | User-Driven Deployment Timing | User-driven deployment exceeding 90 minutes | Feasibility Testing | High | High | Open | QA Team | T006 |  |  |  |  | Yes | May need Pre-Provisioning for some users
I010 | 2024-02-16 | Jennifer Kim | Network Bandwidth Limitations | Slow application downloads affecting deployment time | Network Performance | Medium | Medium | Open | Network Team | T007 |  |  |  |  | No | Consider app size optimization
I011 | 2024-02-17 | Robert Chen | User Experience Complexity | Non-technical users struggling with setup process | User Experience | Medium | High | Open | QA Team | T008 |  |  |  |  | Yes | May require Pre-Provisioning or training
I012 | 2024-02-19 | Michelle Davis | Deployment Mode Decision Criteria | Unclear criteria for selecting deployment mode | Process | High | High | Open | Project Manager | T009 |  |  |  |  | Yes | Need clear decision matrix documentation